# 

# [ ReFeed ]

# Feed Production and Waste Recycling Project

# Statement of Work

## Project Lead:

## Mohamed Rezk Mohamed AAbdelrazek

## Aisha

## Alaa abdeen

## Habiba

## Ibrahim hosny

## Project Sponsor:

## ReFeed Board of Directors / Investors

## Revision History:

| Revision date | Revised by | Approved by | Description of change |
| --- | --- | --- | --- |
| 9 September | CEO | CEO | Parts of the scope |
| 24 October | CEO , CFO , Project manager | CEO | N/A |

## Purpose:

The purpose of the ReFeed project is to establish a sustainable feed production system using local crops and food waste in Egypt.

The project aims to reduce dependency on feed imports, support local agricultural development, and offer an eco-friendly solution to food waste.

## Scope / Major Project Activities:

**1. Agriculture and Feed Manufacturing:**

* Secure local crop and food waste suppliers.
* Develop sustainable agricultural farms.
* Set up and operate a feed manufacturing facility.
* Produce and distribute high-quality feed products for livestock.

**2. Research and Development Facility:**

* Design and construct a research and training center.
* Recruit specialists and conduct research on improving feed quality and agricultural practices.

**3. Digital Application:**

Develop a mobile application for farmers and customers to manage feed orders, track deliveries, and receive farming tips.

## Out-of-scope activities:

* 1. Exporting products to international markets during the initial phase.
* 2. Expanding to non-livestock feed production (e.g., pet food) before project completion.
* 3. Involvement in direct retail sales (limited to B2B and partnerships).

## Deliverables:

* 1. Fully operational feed manufacturing facility.
* 2. Contracts with local crop and food waste suppliers.
* 3. A functioning agricultural research and development center.
* 4. Mobile application for farmers and customers.
* 5. Training programs for farmers and employees on agricultural technologies.

## Schedule Overview / Major Milestones:

**Milestone 1:** Agriculture, Feed Manufacturing, and Distribution Setup

* Secure suppliers and develop farms.
* Set up feed manufacturing facility.
* Duration: 18 months .

**Milestone 2:** Research and Development Facility and Training Programs

* Construct the R&D facility.
* Hire staff and launch training programs.
* Duration: 12 months

**Milestone 3:** Application Development for Farmers and Customers

* Develop app features and complete testing.
* Duration: 6 months

## Estimated hours for completion:

**Estimated total hours for project:**

12,000 hours (including R&D, construction, farming, and app development).

## Estimated date for completion:

## Expected completion date:

## 18 months from the start of the project, considering overlapping milestones.

## If all goes well, the project will be completed within this timeframe.

## 

## 

## 

## Payment Terms

* **1.**Initial payment of 30% upon project approval.
* **2.** 30% upon completion of Milestone
* **3.** 30% upon completion of Milestone
* **4.** Final 10% upon project completion and app launch***.***