## Project Budget
Budget: Project ReFeed
[7 empty] | TARGET BUDGET | ACTUAL/ FINAL SPEND | UNDER/ OVER
[8 empty] | after execution | within execution
[7 empty] | 4M$ to 5.4M$ | excpexted 4M
| LABOR |  |  | MATERIALS |  | FIXED COST | BUDGET | ACTUAL | UNDER/OVER
MILESTONES & TASKS | EMPLOYEE DETAILS | HOURS | RATE | UNITS | $/UNIT
Agriculture, Feed Manufacturing, and Distribution Setup
Task 1: Negotiation and contracting with local farmers and suppliers | Supply chain manager + 10 Labors | 480 hours | 15$ per hour & Labors according to KPIs | N/A | N/A | 15$ per hour | 7200$ | after execution | within execution
Task 2: Develop 15 Agricultural Farms (20 acers per farm)/ (20*6=120*15=1800 per month) | Project manager + 8 Labors | 550 hours | 20$ per hour & Labors according to KPIs | Agricultural Tools: $10,000 total for farming equipment (e.g., tractors, seeders) , and 30.000 per acre | 54M | 54M | 50M | after execution | within execution
Task 3: Design and Test Feed Formulations | R&D manager + 1000 Labors | 480 hours | 15$ per hour & Labors according to KPIs | N/A | 2.6M | 2.6M | 3M | after execution | within execution
-- |  |  |  |  | 56.6 M | 56.6 M | 53 M | 0
Milestone 2 : Research & Development Facility and Training Programs
Task 1 : Design and Construct Facility | Project manager + 10 Labors | 480 | 15$ per hour & Labors according to KPIs | Building tools , workers ..etc | 150,000 $ | 200,000$ | 300.000& | after execution | within execution
Task 2 : Recruit Research and Training Team | Project manager + 23 Labors | 480 | 15$ per hour & Labors according to KPIs | N/A | 10.00$ | 15.000$ | 15,000$ | after execution | within execution
Task 3 : Launch Training Programs | IT manager + 16 Labors | 480 | 15$ per hour & Labors according to KPIs | training tools , Well prepared Halls | 100.000$ | 150.000$ | 200,000$ | after execution | within execution
Task 4 : 15% Integration for food waste in feed manufacturing | R&D managers + 70 Labors | 2880 | 15$ per hour & Labors according to KPIs | New technology tools , well prepared facilities...etc | 1.25M $ | 1M$ | 1.5M$ | after execution | within execution
-- |  |  |  |  | 1.5 M | 1.365 M | 2 M | 0
Milestone 3 : App Development for Farmers and Customers
Task 1 : Define App Features and Scope | Project manager + 30 Labors | 210 | 10$ & Labors according to KPIs | N/A | 50.000$ | 50.000$ | 50.000$ | after execution | within execution
Task 2 : App Development and Testing | Project manager + 40 Labors | 420 | 10$ & Labors according to KPIs | Software & Servers | 250,000$ | 50.000$ | 300.000$ | after execution | within execution
Task 3 : Launching | Project manager + 14 Labors | 270 | 10$ & Labors according to KPIs | N/A | 50.000$ | 50.000$ | 50.000$ | after execution | within execution
-- |  |  |  |  | 350000 | 150000 | 400000 | 0
Reserve buffer | [6 empty] | average 60M$
TOTAL | [7 empty] | 0