## WBS
ReFeed WBS Spreadsheet
Milestone | ID | Task | Owner | Duration (Month)
Agriculture, Feed Manufacturing, and Distribution Setup | 1.1 | Negotiation and contracting with local farmers and suppliers | Supply Chain Manager | 2
| 1.2 | Develop 15 Agricultural Farms (20 acers per farm)/ (20*6=120*15=1800 per month) | Supply Chain Manager | 5
| 1.3 | Design and Test Feed Formulations | R&D Manager | 3
| 1.4 | Set Up Feed Manufacturing Facility | Supply Chain Manager | 4
| 1.5 | Develop Distribution Network | Supply Chain Manager | 2
| 1.6 | Start Initial Production and Distribution | Supply Chain Manager | 2
Research & Development Facility and Training Programs | 2.1 | Design and Construct Facility | R&D Manager | 4
| 2.2 | Recruit Research and Training Team | R&D Manager | 2
| 2.3 | Launch Training Programs | Project Manager | 2
| 2.4 | 15% Integration for food waste in feed manufacturing | IT Manager | 4
App Development for Farmers and Customers | 3.1 | Define App Features and Scope | Project Manager | 1
| 3.2 | App Development and Testing | IT Manager | 4
| 3.3 | Launching | Project Manager | 1