## Refeed Gantt Chart
PHASE THREE
[202 empty] | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[202 empty] | July | [20 empty] | July
[202 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
[202 empty] | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11
Gantt Chart
TITLE: Refeed project | [6 empty] | COMPANY NAME: |  |  |  |  | Refeed
PROJECT MANAGER: Refeed project team | [6 empty] | CREATION DATE: |  |  |  |  | 17/10/2024
TASK ID NUMBER | MILESTONES & TASKS | TASK OWNER | START DATE(ES/LS) | DUE DATE(EF/LF) | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [74 empty] | PHASE TWO | [29 empty] | PHASE THREE | [44 empty] | PHASE FOUR | [14 empty] | PHASE FIVE | [29 empty] | July M 3: PHASE SIX | PHASE SEVEN
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16 |  |  |  |  | WEEK 17 |  |  |  |  | WEEK 18 |  |  |  |  | WEEK 19 |  |  |  |  | WEEK 20 |  |  |  |  | WEEK 21 |  |  |  |  | WEEK 22 |  |  |  |  | WEEK 23 |  |  |  |  | WEEK 24 |  |  |  |  | WEEK 25 |  |  |  |  | WEEK 26 |  |  |  |  | WEEK 27 |  |  |  |  | WEEK 28 |  |  |  |  | WEEK 29 |  |  |  |  | WEEK 30 |  |  |  |  | WEEK 31 |  |  |  |  | WEEK 32 |  |  |  |  | WEEK 33 |  |  |  |  | WEEK 34 |  |  |  |  | WEEK 35 |  |  |  |  | WEEK 36 |  |  |  |  | WEEK 37 |  |  |  |  | WEEK 38 |  |  |  |  | WEEK 39 |  |  |  |  | July M 3: WEEK 40; July M 10: WEEK 41; July M 17: WEEK 42; July M 24: WEEK 43; July M 31: WEEK 44; July M 7: WEEK 45 | WEEK 46 |  |  |  |  | WEEK 47 |  |  |  |  | WEEK 48
[7 empty] | Jan | [22 empty] | Feb | [21 empty] | Mar | [20 empty] | Apr | [8 empty] | May | [22 empty] | Jun | [21 empty] | July | [20 empty] | July | [8 empty] | Aug | [14 empty] | Sep | [20 empty] | Oct | [8 empty] | July M 3: Nov; July T 1: Dec | Jan
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Agriculture, Feed Manufacturing, and Distribution Setup | [5 empty] | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19
1.1 | Negotiation and contracting with local farmers and suppliers | Project Manager | ES=0 LS=5 | EF=2 LF=7 | 2 | 0% | bar: Jan M 1 to Jan F 12
1.2 | Develop 15 Agricultural Farms (20 acers per farm)/ (20*6=120*15=1800 per month) | Supply Chain Manager | ES=0 LS=2 | EF=5 LF=7 | 5 | 0% | bar: Jan M 15 to Jan F 26
1.3 | Design and Test Feed Formulations | R&D Manager | ES=5 LS=7 | EF=8 LF=10 | 3 | 0% | bar: Jan M 29 to Feb F 9
1.4 | Set Up Feed Manufacturing Facility | Supply Chain Manager | ES=0 LS=3 | EF=4 LF=7 | 4 | 0% | bar: Jan M 15 to Jan F 26
1.5 | Develop Distribution Network | Supply Chain Manager | ES=8 LS=10 | EF=10 LF=12 | 2 | 0% | bar: Jan M 15 to Jan F 26
1.6 | Start Initial Production and Distribution | Supply Chain Manager | ES=10 LS=12 | EF=12 LF=14 | 2 | 0% | bar: Jan M 15 to Jan F 26
2 | Research & Development Facility and Training Programs | bar: Jan M 1 to Apr F 11
2.1 | Design and Construct Facility | R&D Manager | ES=0 LS=0 | EF=4 LF=4 | 4 | 0% | bar: Feb M 12 to Feb W 14
2.2 | Recruit Research and Training Team | R&D Manager | ES=4 LS=4 | EF=6 LF=6 | 2 | 0% | bar: Feb R 15 to Feb F 16
2.3 | Launch Training Programs | Project Manager | ES=6 LS=6 | EF=8 LF=8 | 2 | 0% | bar: Feb M 19 to Feb F 30
2.4 | 15% Integration for food waste in feed manufacturing | IT Manager | ES=8 LS=8 | EF=12 LF=12 | 4 | 0% | bar: Feb R 15 to Feb F 16
3 | App Development for Farmers and Customers | bar: Jan M 1 to Apr F 11
3.1 | Define App Features and Scope | Project Manager | ES=0 LS=6 | EF=1 LF=7 | 1 | 0% | bar: Mar M 3 to Mar F 14
3.2 | App Development and Testing | IT Manager | ES=1 LS=7 | EF=5 LF=11 | 4 | 0% | bar: Mar M 17 to Mar F 28
3.3 | Launching | Project Manager | ES=5 LS=11 | EF=6 LF=14 | 1 | 0% | bar: Mar M 31 to Apr F 11