## Stakeholder Analysis
Stakeholder | Role | Involvement | Impact | Power or Influence (H/M/L) | Interest (H/M/L) | Engagement
Chairman | Project sponsor | Investing with resources and Financial support | Wants the project to succeed. No resistance. | H | H | Oversees the project implementation.
Not directly involved. Kept updated on progress and performance.
CEO | Project implementer | Project creator | Invested in the project as a Sr.stakeholder. Possible resistance if there is no financial benefit/outcome | H | H | Project implementation and frequent updates.
CFO | Sr.stakeholder | Financial Management | Highly intrested in project outcome. Possible resistance if there is no financial benefit/outcome. | M | H | Communicate as needed to inform and get feedback.
Investors | Partners | Land and resources providers | Wants the project to succeed. Possible resistance if the project fails. | H | H | Communicate as needed to insure the project is going as agreed.
Project Manager | Manager | Project Implementer | Highly intrested in project success. | M | H | Directly involved as he/she manages the project resources, planning, initiation and execution
No resistance.
Operation Manager | Manager | Project Sustainability | Monitor day to day operations, Sustainablity of production processes | M | H | Responsible for day to day operations
Research and Development Manager | Manager | Tracking Research and Development processes | Responsible for implementation processes | M | H | Responsible for tracking and implementation processes
IT Manager | Manager | Project Technical procedures | Initiating and Implement IT processes and new Softwares | M | H | Manage initiation and implementation for IT processes and new Softwares procedures
Supply Chain Manager | Manager | Manage Production, Manufacturing and Distribution | Prevent Supply Chain delays and Implement manufacturing processes | M | H | Directly involved in Production, Manufacturing and Distribution processes
Farmers | Employees | Resources to implement the project | Have medium power as they are the tool/resource to successfully implement the project. | M | L | Directly involved as they are the manpower resources/tools for successfully implementing the project.
Resistance is high due to lack of knowledge and project minimum outcome.
Co-Farmers | Outsource resources | Resources provided by the investors for farming support and to help implement the project | Have medium power as they are the tool/resource to successfully implement the project. | M | L | Directly involved as they are the manpower resources/tools for successfully implementing the project.
Resistance is high due to lack of knowledge and project minimum outcome.
Employees | Employees | Organizational management | Medium impact.No resistance as they are also resources. | M | L | Involved in the project but they have no authority.

## Power Grid
Keep satisfied (high priority)
Manage closely (high effort)
Monitor (minimum effort)
Show consideration
high
low
high
low
Prioritizing stakeholders (power grid)
Chairman
CEO
CFO
Farmers
Employees
Power
med
Interest
med
Project Manager
Investors
Co-Farmers
Supply Chain Manager
IT Manager
R&D Manager
Operation Manager